## Building CI_CD Plan
Week | DevOps | Deliverable | Difficulty
2024-05-06 | Create Spreadsheet Project Plan Create Trello board | -Project plan Spreedsheet -Trello board | Small
2024-05-13 | Setup Cloud-Based Dev Env + Create project scaffolding + Local test to ensure project build and passing the tests + Take a screenshot showing passing tests after running the `make all` | - A working dev environment in Azure Cloud Shell - A screenshot file showing the passing tests | Medium
2024-05-20 | CI: Configure GitHub Actions + Enable GitHub Action + Modify code with scaffolding + Verify remote test pass in GitHub Actions UI + Take a screenshot of passing GH Action build and put to README.md | - GitHub Actions working on project's repository - A screenshot of GH Action build result. | Large
2024-05-27 | CD: Implement CD on Azure + Add Flask starter code to project + Setup Azure Pipeline to deploy project + Verify Prediction | - A working Azure Pipeline - A working API | Large
2024-06-03 | Finally README Document Create Project Demo Submit project | - A finished README.md - A demo screencast file. - Project submission result | Medium
2024-06-10 | Fix review result in any | - Project submission result | Medium
2024-06-17
2024-06-24
2024-07-01
2024-07-08
2024-07-15
2024-07-22
Goals
Submit the project and pass the review
Quarterly plan
Q2 | Finish the CI/CD with Azure
Q3 | Improve project with Kubernetes
Q4 | Reimplement project with NodeJS
Yearly Plan
Continue improve the project
Implement same solution for the other projects
Formulas:
Week = [Week, row above]+7